ESI 6455 Advanced Engineering Project Management

Spring 2014

Engineering Project Proposal Guidelines

Title page

- The project title is the most important information on the cover page. The title needs to precisely reflect the objective of the project.  It should be centered.

- A project proposal usually consists of two parts: technical proposal and cost proposal.

- Below is a sample Layout of the title page (centered)

# Design and Implementation of a Service Vehicle Positioning Device

A project (technical and cost) proposal submitted to

ABC Company

1234 W. Flagler Street

Miami, FL 33111

Attn: Mr. John British

By

Project Team # 10

Marco Brand (Project Manager or contact)

Antonio Hudson

Maria Martinez

Company Name

Company Address

Contact numbers

January 12, 2014

- Title should be specific, precise, concise, and reflective of the project objective

- Project manager or contact information must be clearly identified in the title page

- No need to use FIU or the company’s logo

Executive Summary page

What is an executive summary?

    - It provides a precise, concise summary of the proposal

    - It is usually one page, no more than 2 pages at the most.

    - It usually highlights each section in a few sentences.

    - It includes no bullet items.

    - It is a non-technical statement designed to provide a quick overview of the full-length report on which it is based.

    - It must have a focus on the proposed technical approach and its merits.

    - For this proposal, you will include key facts about its technical background, problem statement, goal/objectives, deliverables, proposed solution approach, major tasks, duration, budget, merits (profit, benefit, and/or significance).

    - One way to summarize is to take one or two most important sentences from each section of the proposal and organize them in a logical fashion, edit the text so it is cohesive, precise, and brief, while making it stand out among other competing proposals.

    - Remember the importance of the Executive Summary page is only next to the title page. It must impress the reader enough to read further in your proposal.

Table of Contents page

Note:

This page should include the following entries with a page number for each.  “Table of Contents” needs to be on the page top and centered.

- About the company

This section includes:

- Customer corporate history

- Its mission & vision statement

- Nature of business, strategy, competitive priorities

- Overall corporate organizational structure relevant to the project

Note: This section should not be included in a real proposal, but it is a good exercise for this class for learning purpose. A contractor must closely follow and study the customer’s business environment, competition, strategy, and roadmap in order to best address its needs and win contracts.

1.  Introduction

This section describes the problem’s background by giving a relevant non-technical description of the background, which helps situate the problem in the proper context.  It should lead quickly to problem statement (next section). Provide only enough relevant problem background to steer reader’s attention to the problem with a fundamental understanding of its importance and the needs to address it.

2.  Problem Statement

This section presents a formal description of the problem.  It may include a technical definition of the problem.  This includes a direct statement that specifies the intent of the project with both goal and objective statement for the project.

  - Goals: These are long-term goals which usually tied to business strategy or strategic road map of the company, and are in line with the stated problem.  Goals are not to be accomplished by this project alone.  They are often used to entice the reader’s interest in this project. They may be skipped, if there are none when the objective itself is significant enough.

  - Objectives: These are short-term goals to be accomplished by this project.  Objectives must be: “SMART.”

Each objective usually is accompanied with one or multiple deliverables, of which each needs to be sufficiently described including its functionality, technical specifications and requirements.  It could be accompanied with QC/test procedures and/or acceptance criteria at the time of delivery.

Note: Goals and objectives are specific targets or final results.  They are NOT specific actions, tasks, or activities to be engaged in the project, which appear in the solution approach section.

3.  Scope (Constraints, Assumptions, Limits, Exclusions, and Inclusions)

- Scope defines the boundary (domain) of the problem (or system) to take on.  Scope is not the scope of work (SOW); which list work elements.  It is important to properly specify the scope, which defines the extent of your coverage while solving the problem.

- Assumptions and constraints are used to limit and confine the validity and applicability of the proposed solution.  Assumptions usually are general in nature, while constraints are more specific.

- Exclusions and Inclusions are used to further itemize what the project includes or not include.

4. Significance (Merit, profit, and/or benefit)

This section entails the significance of the project.  It is used to underline the importance of the project for solving the problem within its scope as defined.  Profit is the typical focus of significance when it comes to project justification for a for-profit corporate. On the other hand, benefit is the focus of justification for a non-profit company, or public work.  You may argue for its merit from a strategic point of view, which ties to goals, or company mission and vision.  It must underline the importance of the project and why the project is warranted.  It should be as quantifiable as possible, in terms of cost/benefit, cost savings, profit, quality improvement, response time shortening, and/or other benefit due to the project once its objective is reached.

5.  Proposed Approach

This section consists of two subsections.  The first one presents a generic description of a technical solution approach to the problem.  You may outline a number of options first with a pros/cons analysis, and then zoom in to describe/argue for your proposed one.

Based on the solution approach, the second subsection will present a WBS that enlists all significant tasks to be done for this project in a hierarchical manner.  Each task should have a description of the nature of the task, how to do it, and resource types (materials, workers, machines, and tools, etc.) to do with.  If specific expertise, license, or security clearance is required for a task, state so in this subsection as well.

Both subsections are important, They are to impress the reader with your unique solution approach and expertise in this project. The work decomposition process stops at an appropriate level of task detail, such that the proposer (as well as the customer) is able to sufficiently evaluate technical feasibility (and value) of the proposed solution approach; and it needs to sufficiently demonstrates to and convince the customer that you have a superior  technical solution and expertise. In addition, it is detailed enough to lay a convincing foundation for cost and time estimates.  For this proposal, you are expected to decompose the tasks to the OP (work package) level, although it is usually not practical at the proposal stage due to the time and resource available for proposal preparation.

For developing the work breakdown structure (WBS), the breakdown process usually starts from the deliverables and follow their natural boundary and the engineering process.

5.  Contractual aspects

As you develop the WBS, you have to concurrently engage in make/buy decision for each of the sub-deliverables and tasks. For each task or sub-deliverable that is to be outsourced, there is no need to break down the work further. However, outsourcing partners and contractual matters need to be considered, including the entire chain of command down to your suppliers and vendors.  The issue of quality assurance and timely delivery needs to be considered as well.  These decisions form the foundation for sub-contracting. This section is designated for explaining contractual needs and their related risk and uncertainty.  You may also include the issues of reporting requirements, IP/proprietary requirements, etc. in this section.

6.  Resources

This section identifies each resource type (equipment, tools, workers, machines, software, etc) and the amount of time, required to perform each WBS task.  A practice is that you would create a table, listing all WBS tasks in the rows and identifying all resource types in the columns with a unit of measurement (UOM). Their corresponding cells are then used to record the amount of time required for each task.

7. Costs

After the amount of each resource requirement for each task is estimated. You need to estimate and assign a unit cost for each resource type to estimate the cost for each task by each resource type.  You will then consider adding direct overhead for project management, and then adding general overhead for the company plus profit, if any.  These two overheads are usually in form of a percentage of the direct cost.

You may consider splitting the cost of each type into two columns, one for the customer to pay, and the other is for the proposing company to absorb, in case you want to show cost sharing for any reason (say, strategic collaboration).

8.  Schedule

You will need to present a PROJECT MASTER SCHEDULE (PMS) based on your WBS.  The PMS should include all the WBS activities for this project.  A Gantt chart is usually used to present the schedule.  Microsoft Project is a software tool with Gantt chart function.  If milestone events exist, they should be included in the schedule.

In addition to the Gantt chart, you need to add narratives to describe the schedule and points out major events and milestones. Simply presenting an M/S Gantt chart without sufficient verbal description is not sufficient and is rude to the reader.  When the WBS is huge and complicated, you may consider using multiple Gantt charts for various levels of schedule details.

9.  Budget

The budget builds on the cost table and schedule. It summarizes the expenditure plan by tasks defined in the WBS and over the project horizon (according to the schedule).

10. Personnel

This section should include several subsections: (1) organizational structure for this project, (2) job description and qualification/skill requirements, (3) linear responsibility chart, and (4) communication plan.

Both the organization chart and job description should use role and job function, instead of real team members’ name, because team members may not come on board yet, plus they may come and go often.  Include only those that are going to perform WBS tasks.  The project manager should be on the top of the organization chart for this project.

The Linear Responsibility Chart is used to indicate who is responsible for what to do each task. Identify all possible roles, and then for each task you identify who will play which role.

Communication plan outlines communication channels and report types to be generated by whom and submitted to whom, how and how often.

11. Evaluation methods

This section details your plan for quality evaluation of each deliverable (and the project) at the time of delivery.  This is a plan to be agreed upon by all parties, so rules will not be changed at the last moment; it will be difficult if you disagree on the measurement of the deliverable.  The method should include its procedure and tools to use.  For qualitative measures, you may devise a quality checklist or weighed quality measurement matrix to measure accomplishment of the proposed objective.  Each objective and its deliverable(s) should have an evaluation plan proposed in the proposal.  Again, the plan should be based on the quality requirements or technical specifications as stated in the objective section.  In addition to the method design itself, you also need to identify the evaluation agency or evaluators.

12.  Potential problems (external risks)

During the project execution phase, there could be potential problems (risks) that may arise.  This section is used to point out potential uncertainties and difficulties (technical failure, strikes, weather-type deadlines, subcontractor defaults, etc.)  that would happen and thus affect the project.  You need to identify risks, assess its likelihood and potential outcome should they occur, and proposed a contingency plan and tracking mechanisms for each deemed significant.  A risk has to be outside of the project team’s control.  It may or may not be the contractor’s sole responsibility, but it should be identified and dealt with in your contingency plan.  If there are no risks, you say, “There are no risks associated with this project.”

13.  Appendix

References (citations)

Resumes

Certificates and licenses

Comments on overall project proposal:

- Use consistent fonts and format throughout the report.

- Use technical precise, concise, brief- to-the-point statements.

- Avoid using words such as “we”, “our”, “us”, “they”.  Instead, use “the team”, “the company”, or “the contractor.”

- Spell check please!  Use grammar check too!

- Label all figures and tables with figure/table # and caption

- Any additional document may be included in the appendix section, including the list of references (citation in the text), detailed schedules and budgets, corporate licenses and certificates, lists of projects completed prior to this proposal, resumes of principle personnel on this proposed project.

- This project proposal exercise is intended to be inclusive and through.  However, for a real proposal, you will exercise prudence to decide which sections to be included and at what level of details.